## Slide 1: End-to-End Data Analytics Project for Business Solutions CHINENYE NORA OKEY
14
05
2025

## Slide 2: Agenda
Project Overview
Timeline & Milestone
Roles & Responsibilities
Communication Plan
Risk Management

## Slide 3: PROJECT OVERVIEW

## Slide 4
PROJECT OVERVIEW
Deliverables:
Cleaned HR dataset
Structured data tables (Fact and Dimension tables)
HR Dashboard
Project Report/Documentation
This project aims to develop a data-driven HR dashboard to help the HR team make strategic decisions about employee demographics, attrition, and recruitment.
Scope: This project includes data cleaning, transformation, visualization, and analysis using Excel and Power BI. It excludes backend system integration.

## Slide 5
TIMELINE & MILESTONE

## Slide 6
TIMELINE & MILESTONE
Phase | Start Date | End Date | Milestone
Project Planning | May 14, 2025 | May 15, 2025 | Project plan finalized
Data Collection & Cleaning | May 16, 2025 | May 18, 2025 | Cleaned dataset ready
Data Analysis | May 19, 2025 | May 22, 2025 | Completed analysis & answered business questions
Dashboard Development | May 23, 2025 | May 26, 2025 | Dashboard completed
Final Documentation | May 27, 2025 | May 28, 2025 | Report ready for submission
Review & Delivery | May 29, 2025 | May 30, 2025 | Project reviewed & delivered

## Slide 7: ROLES & RESPONSIBILITIES

## Slide 8
ROLES & RESPONSIBILITIES
Team Member | Role | Responsibilities
Chinenye Nora | Project Lead / Analyst | Data cleaning, analysis, dashboard creation, reporting
[Optional teammate] | QA Reviewer | Review dashboard accuracy, validate insights
[Mentor/Coach] | Project Advisor (if any) | Guide analysis process and provide feedback

## Slide 9: COMMUNICATION PLAN

## Slide 10
COMMUNICATION PLAN
Tools Used:
Email for formal communication
WhatsApp or Slack for daily/quick updates
Google Docs/Sheets for documentation
Zoom/Meet for reviews and feedback sessions
Frequency
Activity | Frequency | Channel
Daily progress updates | Daily (if team) | WhatsApp
Status meeting/review | Twice a week | Zoom/Meet
Final review and handoff | At project close | Zoom/Meet
Documentation sharing | As completed | Google Drive

## Slide 11: RISK MANAGEMENT

## Slide 12
RISK MANAGEMENT
Potential Risk | Impact Level | Mitigation Strategy
Delays in data collection or cleaning | High | Allocate buffer time in schedule
Technical issues with tools (Excel, Power BI) | Medium | Have backup tools (e.g., Google Sheets, Tableau Public)
Lack of clarity in requirements | High | Clarify goals early, maintain open communication
Data quality issues (missing/inaccurate data) | High | Use data validation methods; communicate with data owners
Time constraints/conflicting commitments | Medium | Set realistic deadlines, prioritize key deliverables

## Slide 13: Thank you
CHINENYE NORA OKEY
09019443428
  queennoraokey@gmail.com